## Performance in Delivering
Id | Research Ethics Committee Reference Number | Name of Trial | Target number of patients available | Target number of patients | Date Agreed to recruit target number of patients available | Date Agreed to recruit target number of patients | Trial Status | Target met within the agreed time | Comments
57057 | 13/SC/0628 | A randomized, doubleblind, placebocontrolled, parallelgroup proof of concept study to evaluate the effect of AFQ056 in Obsessive Compulsive Disorder (OCD) patients resistant to Selective Serotonin Reuptake Inhibitor (SSRI) therapy placebocontrolled, parallelgroup proof of concept study to evaluate the effect of AFQ056 in Obsessive Compulsive Disorder (OCD) patients resistant to Selective Serotonin Reuptake Inhibitor (SSRI) therapy | Available | 6 | Available | 2015-02-13 | Suspended | N/A | suspended by sponsor
57058 | 14/SC/0037 | A Phase iii, Randomized, Double-Blind, Placebo-Controlled, Parallel-Group, Multicenter, Efficiacy And Safety Study Of Gantenerumab In Subjects With Mild Alzheimer's Disease | Available | 6 | Available | 2019-04-15 | Open | N/A | currently have 2 being screen to assess suitability for randomisation
57059 | 12/LO/1498 | A Phase Ii, Multicenter, Randomized, Doubleblind, Parallelgroup, Placebocontrolled Study To Investigate The Efficacy And Safety Of Ro4602522 Added To The Background Therapy Of The Acetylcholinesterase Inhibitors Donepezil Or Rivastigmine In Patients With Moderate Severity Alzheimer’s Disease | Available | 6 | Available | 2013-10-17 | Open | N/A
57060 | 12/SS/0138 | REstart or STop Antithrombotics Randomised Trial (RESTART) | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A | No recruitment, follow up data only
57061 | 12/EM/0324 | Rehabilitation of Memory following Traumatic Brain Injury – a Phase III Randomised Controlled Trial | Available | 25 | Available | 2015-06-30 | Open | N/A