## Performance in Initiating
Id | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
57987 | 12/EM/0324 | Rehabilitation of Memory following Traumatic Brain Injury – a Phase III Randomised Controlled Trial | 2014-09-09 | 2014-09-24 | Yes | 2014-11-25 | 15 | 62 | 77 | No | [10 empty] | tbc | NHS Provider
57989 | 14/LO/0736 | Valuing Active Life in Dementia (VALID) Work Packages 3/4: a pilot trial and randomised controlled trial of Community Occupational Therapy in Dementia (COTiD­UK) | 2014-10-06 | 2014-10-10 | Yes | 2014-11-12 | 4 | 33 | 37 | Yes | [11 empty] | Please Select...
57990 | 13/LO/1595 | Cognitive behavioural therapy vs standardised medical care for adults with Dissociative non­Epileptic Seizures: A multi­centre randomised controlled trial (CODES) | 2014-12-04 | 2014-12-18 | No |  | 14 |  |  | No | [5 empty] | Y |  |  |  |  | SHSC involvement is not for at least 3 months after study starts at referring hospital | Sponsor
60684 | 15/EM/0014 | The BEADS Feasibility Pilot Trial | 2015-05-06 | 2015-05-20 | No |  | 14 |  |  | Within 70 Days | [11 empty] | Please Select...