## PII
Id | REC Reference Number | IRAS Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
95602 | 16/NW/0014 | 177971 | NHS Permission | Effects of Enhanced Home Treatment Care on the Speed of Recovery and Length of Inpatient Stay in Psychiatric Patients: A Randomised Controlled Pilot Trial | 2016-01-22 | 2016-01-28 | Yes | 2016-02-01 | 6 | 4 | 10 | Yes | [5 empty] | Please Select... | [12 empty] | Please Select...
95603 | 15/SC/0714 | 192332 | NHS Permission | A Phase 3, double-blind, randomized study of RVT-101 versus placebo when added to existing stable donepezil treatment in subjects with mild to moderate Alzheimer's disease. | 2016-02-17 | 2016-02-17 | Yes | 2016-05-16 | 0 | 89 | 89 | No | [5 empty] | Please Select... |  |  |  |  | Y | [6 empty] | Sponsor delay in arranging Site Initiation Visit. | Sponsor
95608 | 16/SC/0256 | 204750 | HRA Approval | RVT-10103002 OLE GBR 064 |  |  | No |  |  |  |  | No | 2017-01-17 |  | 2016-10-07 | 2017-01-18 | 2017-01-25 | Please Select... | [12 empty] | Please Select...
95609 | 16/SC/0363 | 205067 | HRA Approval | Randomised, double-blind, placebo controlled, multi-centre registration trial to evaluate the efficacy and safety of TTP488 in patients with mild Alzheimer's |  |  | Yes | 2016-12-16 |  |  |  | No | 2016-09-22 | 2016-09-22 | 2016-10-04 | 2016-11-22 | 2016-12-16 | Please Select... | [12 empty] | Please Select...
95610 | 16/YH/0238 | 199383 | HRA Approval | Journeying through Dementia |  |  | Yes | 2017-01-12 |  |  |  | No | 2016-10-26 | 2016-10-26 | 2016-08-25 | 2016-10-26 | 2016-12-16 | Please Select... | [12 empty] | Please Select...

## PID
Id | REC Reference Number | IRAS Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
17441 | 14/SS/0049 | 143780 | A Randomized, Double-Blind, Placebo-Controlled, Parallel-Group, 26-Week, Phase 3 Study of Two Doses of EVP-6124 or Placebo in Subjects with Mild to Moderate Alzheimer's Disease Currently or Previously Receiving an Acetylcholinesterase Inhibitor Medic | Not Available / Not Agreed |  |  | Date Agreed | 2016-06-09 | 0 | 2016-06-09 | 0 | Withdrawn By Sponsor